## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048D |  | Project Name: |  | Caliber Collision
NPDES Id. No. | NMR10067L |  | Location: |  | 250 98th St NW
2024-08-07 |  | Owner |  |  |  | Contractor
Operator |  | Cross Development CC Albuquerque, LLC
Contact name & title |  | Meagan Vieren
e-mail |  | Meagan@crossdevelopment.net
Contact Phone # |  | 352-871-8953
COA Inspector |  | Doug Hughes | [8 empty] | Rain
Construction Phase: |  | grading | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-27 |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI - This site is a 2.5-acre part of a 10.5-acre “Common Plan of Development or Sale” (CPD) covered by permit NMR10050Y, owner/operator “RS Bluewater, LLC”, that commenced 2 years ago. The ownership of this 2.5-acre portion of the site was transferred to “Cross Development CC Albuquerque, LLC” when the special warrant deed was recorded on April 3, 2024. The new owner failed to file its NOI by the deadline in Violation of CGP 1.4.3. The NOI hasn't been approved by the City in Violation of ordinance § 14-5-2-11(A) Required Mitigation: The property owner’s NOI and ESC Plan must be submitted to the City of Albuquerque for review and approval per Albuquerque’s Erosion and Sediment Control (ESC) ordinance § 14-5-2-11(A).
2 | Stabilization—The only vegetation on the site is weeds, which are taller and wider than 6" in violation of the Weed, Litter and Snow Removal Ordinance (§ 9-8-1).Weeds are annual vegitation and do not satisfy any part of CGP 2.2.14. Required Mitigation: Stabilize the inactive disturbed areas and “large bare areas” per CGP 2.2.14.c.i. Implement and maintain stabilization measures in areas that remain inactive for 14 days or more. Measures must be initiated within 14 days and completed no later than 14 days per CGP 2.2.14.
3 | Posting - CGP coverage was not posted so it is visible from the public road nearest to the active part of the construction site, using a font large enough to be readily viewed from a public right-of-way in violation of CGP 1.5. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
4 | SWPPP- No personnel were present onsite and there wasn't a sign identifying the location of the SWPPP and self-inspection reports in violation of CGP 7.3. I called Meagan Vieren and left a message but no responce so the SWPPP and self-inspection reports were not available on-site during the inspection in Violation of CGP 7.3, City Ordinance § 14-5-2-11(C)(1), and CGP 4.7.3. Required Mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | ?
Notes:
The SWPPP was not on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action