## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048E |  | Project Name: |  | Goodwill
NPDES Id. No. | NMR1006R2 |  | Location: |  | 270 98th St NW
2025-03-12 |  | Owner |  |  |  | Contractor
Operator |  | Goodwill Industries of New Mexico |  |  |  | Architectural Contractors Inc
Contact name & title |  | Shauna Kastle CEO |  |  |  | Scooter Haynes
e-mail |  | skastle@goodwillnm.org |  |  |  | Scooter@scmpartners.com
Contact Phone # |  | 505-881-6401 ext 9 |  |  |  | 898-6622
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:15am |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP has not been certified by both operators in violation of CGP Part 7.2.10. The self-inspection reports were not available during the inspection in violation of CGP Part 4.7.3. The NOI for Architectural Contractors Inc is missing from the SWPPP in violation of CGP Part 7.2.11 Required mitigation: Both signatories must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11 per CGP Part 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3. Once you are authorized for CGP coverage, you must include a copy of your NOI submitted to the EPA per CGP Part 7.2.11.
2 | Sediment has been tracked-out of your site onto the access road leading to Bluewater Rd in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which the track-out occurs or by the end of the next business day if track-out occurs on a non-business day per CGP Part 2.2.4.d. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces, or by using other similarly effective means of sediment removal. You are prohibited from hosing or sweeping tracked-out sediment into any constructed or natural site drainage feature, storm drain inlet, or receiving water.
3 | There are several areas with concrete washout on bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Re-install stormwater controls around perimeter and construction exits. Ensure that the inspection reports are signed by both operators.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action