## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048E |  | Project Name: |  | Goodwill
NPDES Id. No. | NMR1006R2 |  | Location: |  | 270 98th St NW
2024-10-21 |  | Owner |  |  |  | Contractor
Operator |  | Goodwill Industries of New Mexico |  |  |  | Architectural Contractors Inc
Contact name & title |  | Shauna Kastle CEO |  |  |  | Scooter Haynes
e-mail |  | skastle@goodwillnm.org |  |  |  | Scooter@scmpartners.com
Contact Phone # |  | 505-881-6401 ext 9 |  |  |  | 898-6622
COA Inspector |  | James Hughes |  |  |  | Time |  | 9AM |  |  |  | Rain
Construction Phase: |  | Plunbing & footers | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2029-10-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI - At the time of the inspection, debris, dirt, and vegetation had been scraped into piles signaling the Commencement of Construction Activities as defined in Appendix A of the Environmental Protection Agency's (EPA's) Construction General Permit (CGP) where it says "the initial disturbance of soils (or ‘breaking ground’) associated with clearing." The construction activities commenced before the city approved the property owner's NOI and ESC Plan in Violation of City Ordinance § 14-5-2-11(A). The city provided comments on 9/20 and 10/18 in response to the property owner's application, which said the ESC Plan was incomplete, missing proper BMPs and construction details. Required Mitigation: The property owner’s NOI and ESC Plan must be resubmitted to the City of Albuquerque for review and approval per Albuquerque’s Erosion and Sediment Control (ESC) ordinance § 14-5-2-11(A).
2 | Posting - CGP coverage was not posted so it is visible from the public road nearest to the active part of the construction site, using a font large enough to be readily viewed from a public right-of-way in violation of CGP 1.5. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
3 | SWPPP - No personnel were present onsite at the time of the inspection, and the required notice of the SWPPP location wasn't posted in violation of CGP7.3. So, the SWPPP and self-inspection reports couldn't be checked on-site in Violation of CGP 7.3, City Ordinance § 14-5-2-11(C)(1), and CGP 4.7.3. Required Mitigation: The SWPPP, including the SWPPP Map, Self-Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
4 | BMPs - Perimeter Silt Fence (SF) was in place, but the Construction Exit (CE) was missing. The site drains to the Southeast Corner, where concentrated flow exits the site. The SF in the SE Corner is inadequate for concentrated flow. Additional stormwater controls are not designed in violation of CGP 2.1.4, which requires the Operator to "Design and install all stormwater controls in accordance with good engineering practices, including applicable design specifications." The installation of the stormwater controls wasn't complete before the beginning of Construction Activities in Violation of CGP 2.1.3. Required mitigation: Additional stormwater controls, ponds, berm, and CE must be designed and installed in accordance with CGP 2.1.4 no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
5 | Stabilization—About half of the perennial vegetation was removed from this site in a 35' wide strip around the edges plus about 0.25-acre pad site in the south 80 of the site as part of the subdivision development that started in late 2022, and this site was still under permit coverage when Goodwill purchased it on 12/29/2023. The edges were Hydromulched in mid-2023 but didn't grow significant perennial vegetation, and the mulch had large bare spots before the end of 2023. The pad had thin spotty gravel cover in Aug 2024. At the time of the inspection on 10/21/24, the previously disturbed area had been scraped, moving vegetation and trash into piles, but the area of native vegetation remained undisturbed in the center third of the lot. Required Mitigation: Stabilize the disturbed areas that remain inactive for 14 days or more per CGP 2.2.14.c.i. Measures must be initiated within 14 days and completed no later than 14 days per CGP 2.2.14.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | none
Notes: | This inspection was conducted 2 days after a 0.36" rain but no discharge.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action