## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048F |  | Project Name: |  | Stripes Burrito
NPDES Id. No. |  |  | Location: |  | 260 98th St NW
2025-06-03 |  | Owner |  |  |  | Contractor
Operator |  | Stripes Real Estate LLC
Contact name & title
e-mail
Contact Phone #
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:15am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-02 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | NOI - Land disturbing activities have occurred prior to the City SWQ approval and has led to an unauthorized stormwater discharge in violation of City Ordinance §14-5-2-11 and CGP Part 1.4 Required mitigation: For projects that disturb one acre or more, the property owner is to provide the Construction General Permit (CGP) Electronic Noitice of Intent (eNOI) documentation that contains the property owner name and contact information a minimum of 14 days prior to earth disturbance and prior to obtaining Work Order or Building Permit approval per City Ordinance §14-5-2-11. All “operators” (i.e. owners and contractors) associated with your construction site must submit to the EPA a complete and accurate NOI prior to commencement of construction activities per CGP Part 1.4.
2 | Posting - CGP coverage must be posted at all construction sites greater than 1 acre in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
3 | SWPPP - The current Stormwater Pollution Prevention Plan (SWPPP) and self-inspection reports were not available during the inspection in violation of CGP Parts 7.3 and 4.7.3. Required mitigation: You must keep a copy of the up-to-date SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. If an on-site location is unavailable to keep the SWPPP (and inspection reports) when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site.
4 | BMPs - There were no stormwater controls installed at the site to prevent sediment discharge in violation of CGP Part 2.1.3. Required mitigation: Complete installation of stormwater controls by the time each phase of construction activities has begun per CGP Part 2.1.3.
5 | Sediment - Sediment on paved surfaces from drive way in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited material by the end of the same business day or by the end of the next business day if it occurs on a non-business day per CGP Part 2.2.4. Remove by sweeping, shoveling, or vacuuming these surfaces. You are prohibited from hosing or sweeping the material into storm conveyances.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N?A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action