## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048F |  | Project Name: |  | Stripes Burrito
NPDES Id. No. | NMR1007KZ |  | Location: |  | 260 98th St NW
2026-02-05 |  | Owner |  |  |  | Contractor
Operator |  | Stripes Real Estate, LLC
Contact name & title |  | Saurabh (Sam) Agrawal
e-mail |  | sam@vkcmanagement.com
Contact Phone # |  | 281-948-2125
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Signage, interiors | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports are still unavailable during the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
It appears that the exterior construction is near completion; only a small portion of disturbed land remains. Once all areas have been permanently stabilized (e.g. landscaping or paving), please terminate your CGP coverage by filing your NOT with the EPA and request a Determination of Stabilization from the City.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action