## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E050 |  | Project Name: |  | Bluesky Distributing Tract 9B
NPDES Id. No. | NMR10051D |  | Location: |  | Bluewater Rd and Daytona Rd
2023-06-05 |  | Owner |  |  |  | Contractor
Operator |  | Aspen and Autumn LLC
Contact name & title |  | Robert Poole
e-mail |  | blueskyrobert@yahoo.com
Contact Phone # |  | 263-4047
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-02-15 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Your NPDES permit coverage was not posted for public viewing. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5.
2 | Your SWPPP was not available on-site at time of inspection, nor was a sign posted giving the location of your SWPPP. Your SWPPP must be kept up-to-date per CGP 7.1 and available on-site per CGP 7.3. If an on-site location is unavailable to keep your SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-06-01
Notes:
Land has been disturbed on property and construction has begun on a new access road.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action