## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E050 |  | Project Name: |  | Bluesky Distributing Tract 9B
NPDES Id. No. | NMR10051D |  | Location: |  | Bluewater Rd and Daytona Rd
2023-08-02 |  | Owner |  |  |  | Contractor
Operator |  | Aspen and Autumn LLC
Contact name & title |  | Robert Poole
e-mail |  | blueskyrobert@yahoo.com
Contact Phone # |  | 263-4047
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP Certification is still missing a signature from Aspen and Autumn LLC. Aspen and Autumn, LLC also needs to be added to the list of operators along with their area of control and stabilization strategy for the South Lot. Required mitigation: CGP Part 7.2 lists the required SWPPP contents which include All Site Operators and the areas of the site over which each operator has control (CGP Part 7.2.1) and Descriptions of Stormwater Controls including stabilization measures (CGP Part 7.2.6.b.vii). Aspen and Autumn, LLC also needs to certify the SWPPP with the signatory and date the SWPPP in accordance with Appendix G, Part G.11 (CGP Part 7.2.10).
2 | BMPs in need of repair. The silt fence along Daytona Road needs to be re-staked. Required mitigation: Ensure all stormwater controls are maintained and remain in effectivve operating condition during permit coverage and are protected from activities that would reduce their effectiveness as per CGP Part 2.1.4.
3 | The pond on the east side of the southern lot is partially stabilized. The southern lot and northern lot disturbances require stabilization that should be initiated if construction activities have perminently ceased or will be inactive for 14 or more calendar days. Required mitigation: Complete the pond and southern lot stabilization as required in CGP Part 2.2.14.
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-07-13
Notes:
Previous inspection violations were all mitigated: NOI is both posted and located in SWPPP located at active construction site north of lot (Titan (Spec) 150K) but still needs to certify SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action