## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E050 |  | Project Name: |  | Bluesky Distributing Tract 9B
NPDES Id. No. | NMR10051D |  | Location: |  | Bluewater Rd and Daytona Rd
2023-08-30 |  | Owner |  |  |  | Contractor
Operator |  | Aspen and Autumn LLC
Contact name & title |  | Robert Poole
e-mail |  | blueskyrobert@yahoo.com
Contact Phone # |  | 263-4047
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9:30am |  |  |  | Rain
Construction Phase: |  | infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-08-10
Notes: | SWPPP located in building on north lot. In process of stabilizing
Previous inspection violations were all mitigated: NOI is both posted and located in SWPPP located at active construction site north of lot (Titan (Spec) 150K) but still needs to certify SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action