## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E051 |  | Project Name: |  | Titan (Spec) 150K
NPDES Id. No. | NMR1004R6 |  | Location: |  | Daytona and Bluewater Rd
2023-08-02 |  | Owner |  |  |  | Contractor
Operator |  | Westpoint 40, LLC |  |  |  | Wilger Construction
Contact name & title |  | Brian Patterson |  |  |  | Tim Lindgren
e-mail |  | bpatterson@titan-development.com |  |  |  | tlindgren@wilger.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-239-0246
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Paving, landscaping, interior | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs in need of repair. The silt fence along Daytona Road needs to be re-staked. Required mitigation: Ensure all stormwater controls are maintained and remain in effectivve operating condition during permit coverage and are protected from activities that would reduce their effectiveness as per CGP Part 2.1.4.
2 | The pond on the east side of the southern lot is partially stabilized. The southern lot and northern lot disturbances require stabilization that should be initiated if construction activities have perminently ceased or will be inactive for 14 or more calendar days. Required mitigation: Complete the pond and southern lot stabilization as required in CGP Part 2.2.14.
3 | A dirt ramp was found on the corner of Daytona Road and Bluewater Road. This ramp is located directly next to a stormwater curb inlet. The inlet protection needs repair. The City does not allow dirt ramps of any kind. Required mitigation: You must minimize track-out and use appropriate stabilization techniques at all points that exit onto paved roads, per CGP Part 2.2.4. You must protect storm inlets per CGP Part 2.2.10.
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-07-13
Notes: | Tim has SWPPP inside building
Previous inspection found out-of-date SWPPP and missing inspection reports (some issues with SWPPP were resolved), BMP maintenance/repair, and NOI posting. The silt fence on the west side of Daytona has been dmaged by wind and/or vehicles twice.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action