## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E051 |  | Project Name: |  | Titan (Spec) 150K
NPDES Id. No. | NMR1004R6 |  | Location: |  | Daytona and Bluewater Rd
2023-08-30 |  | Owner |  |  |  | Contractor
Operator |  | Westpoint 40, LLC |  |  |  | Wilger Construction
Contact name & title |  | Brian Patterson |  |  |  | Tim Lindgren
e-mail |  | bpatterson@titan-development.com |  |  |  | tlindgren@wilger.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-239-0246
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9:30am |  |  |  | Rain
Construction Phase: |  | Paving, landscaping, interior | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP is missing a Corrective Action Log
2 | There is a dirt ramp next to construction site and in vicinity of a stormwater inlet
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-08-10
Notes: | Tim has SWPPP inside building, currently in process of stabilizing
Previous inspection found out-of-date SWPPP and missing inspection reports (some issues with SWPPP were resolved), BMP maintenance/repair, and NOI posting. The silt fence on the west side of Daytona has been dmaged by wind and/or vehicles twice.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action