## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E051 |  | Project Name: |  | Titan (Spec) 150K
NPDES Id. No. | NMR1004R6 |  | Location: |  | Daytona and Bluewater Rd
2023-10-12 |  | Owner |  |  |  | Contractor
Operator |  | Westpoint 40, LLC |  |  |  | Wilger Construction
Contact name & title |  | Brian Patterson |  |  |  | Tim Lindgren
e-mail |  | bpatterson@titan-development.com |  |  |  | tlindgren@wilger.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-239-0246
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 3:15pm |  |  |  | Rain
Construction Phase: |  | Stabilizing | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-09-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
2.1 | Discharge off site? (Y/N) |  |  | No | [5 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date:
Notes:
Stabilization in progress, BMPs still in place. Remove BMPs, terminate coverage, and request a Determination of Stabilization to cease self-inspection requirement.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action