## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E011 |  | Project Name: |  | ABB ABQ Expansion
NPDES Id. No. | NMR100637 |  | Location: |  | 6625 Bluewater Rd NW
2024-07-09 |  | Owner |  |  |  | Contractor
Operator |  | ABB Installation Products Inc. |  |  |  | David E. Harvey Builders, Inc.
Contact name & title |  | David Jaramillo |  |  |  | David Brown
e-mail |  | david.jaramillo@us.ab.com |  |  |  | jshockley@harveybuilders.com
Contact Phone # |  | 505-833-2637 |  |  |  | 713-262-5685
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3:45pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-30 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-07-01
Notes:
The SWPPP was located in the construction office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action