## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E023L |  | Project Name: |  | Bluewater Galleria Mall
NPDES Id. No. | NMR1005V5 |  | Location: |  | 531 Silver Creek Rd NW
2024-07-02 |  | Owner |  |  |  | Contractor
Operator |  | MJ Hospitality LLC |  |  |  | None on file
Contact name & title |  | Mohamed Jasser
e-mail |  | jasser007@gmail.com
Contact Phone # |  | 505-385-9911
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-30 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The permit coverage posting was not located during the inspection in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, as per CGP Part 1.5.
2 | The SWPPP and self-inspection reports were not available at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location, so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
3 | BMPs - The perimeter silt fence is missing sections and is in disrepair in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date: |  | N/A
Notes:
Construction entrance is at the southwest corner of the property on Unser Blvd SW.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action