## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E058_B |  | Project Name: |  | Nuevo Atrisco
NPDES Id. No. | NMR1005LO |  | Location: |  | 201 Unser Blvd NW
2024-05-23 |  | Owner |  |  |  | Contractor
Operator |  | Nuevo Atrisco, LLC |  |  |  | Wilger
Contact name & title |  | Ron Douglas |  |  |  | Tim Lindgren
e-mail |  | ron@mdgrealestate |  |  |  | jwilger@wilger.com
Contact Phone # |  | 505-585-3111 |  |  |  | 505-345-2854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1230pm |  |  |  | Rain
Construction Phase: |  | verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The self inspection reports were not signed by the owner in violation of CGP Part 4.7.2. A delegation of authority to Tim Lindgren of Wilger Construction is not acceptable by the EPA as it is a third party to Nueva Atrisco LLC. Required mitigation: Each inspection report must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11 per CGP Part 4.7.2.
2 | The track-out pads were not placed at the construction entrance in violation of CGP Part 2.2.4. Required mitigation: Use appropriate stabilization techniques at all points that exit onto paved roads per CGP Part 2.2.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 4/30/2024*
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action