## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E060 |  | Project Name: |  | 7200 Bluewater
NPDES Id. No. | NMR1003UT |  | Location: |  | 7200 Bluewater
2021-07-27 |  | Owner |  |  |  | Contractor
Operator |  | M & B Investments Ltd. Co. |  |  |  | GA Brunacini Construction
Contact name & title |  | Angelo Brunacini |  |  |  | Angelo Brunacini
e-mail |  | abrunacini@brunacini.com |  |  |  | abrunacini@brunacini.com
Contact Phone # |  | 505-833-2928 |  |  |  | 505-833-2928
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-07-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Permit coverage was not properly posted, ID # missing from sign, phone numbers on sign don't have SWPPP, Location of SWPPP not identified. | [9 empty] | 2021-05-03
2 | SWPPP was not onsite though it eventually got there. It must be available onsite, and up-to-date. Map missing, Owner/Operator NOI and certification missing. SWQ Team not identified.
3 | Trackout and sediment in the street at entrance and near inlets. Water truck started washing street sediment into curb and maybe into inlets. Pickup and remove sediment from street and sidewalk daily. Never wash it into inlets!
4 | 10' hole in north silt fence needs repair
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | yes | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-07-04
Notes: | Pad grading finished. Stem wall south not started yet. Trackout at hydrant on SE corner.
Entrance moved to SE corner.
Borrow site Inspections missing, Franklins NOI for borrow in this SWPPP but no map?
Borrow site has a separate SWPPP and a separate owner. G&D for APS Bus storage submited, so
who ownes the borrow site?
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action