## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E060 |  | Project Name: |  | 7200 Bluewater
NPDES Id. No. | NMR1003UT |  | Location: |  | 7200 Bluewater
2022-02-28 |  | Owner |  |  |  | Contractor
Operator |  | M & B Investments Ltd. Co. |  |  |  | GA Brunacini Construction
Contact name & title |  | Angelo Brunacini |  |  |  | Angelo Brunacini
e-mail |  | abrunacini@brunacini.com |  |  |  | abrunacini@brunacini.com
Contact Phone # |  | 505-833-2928 |  |  |  | 505-833-2928
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: | 3pm |  |  |  | Rain
Construction Phase: |  | Earthwork | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-01-01 |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | Permit coverage was not properly posted, dsign was laying on the ground but still ledgible. | [8 empty] | 2021-05-03
2 | Minor washout next to the container needs disposed in the waste container.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | yes | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action