## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Murphy Express - Unser/Central
Location: |  |  | 221 Unser Blvd. SW
Site Contact Name & Agency | [6 empty] | ESC File No. | K10E061
[7 empty] | NPDES Id. No. | NMR1002SY
Owner | [6 empty] | Phone: (o)
Owner's e-mail | [6 empty] | Phone: (m)
Inspection Date: |  |  | 2020-06-25 | Start/End Time: |  | 0900/0920hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | eaerthwork & infrastructure | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 72* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2020-06-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | re-post NPDES posting
2 | Please provide latest SWPPP self-inspection report.
3 | Clarify and provide:
3a. | Contractor and point of contact with e-mail
3b. | Clarify Owner information. Conflicting information on owner's NOI and information sheet provided
to SWQ.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | requested |  | Latest report Date: |  | not on file
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2020-06-25

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action