## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E061 |  | Project Name: |  | Murphy Express
NPDES Id. No. | NMR1002W2 |  | Location: |  | 221 Unser Blvd. | [6 empty] | terryrigdon@murphyusa.com
2021-07-01 |  | Owner |  |  |  | Contractor
Operator |  | Armstrong Central Unser Blvd |  |  |  | Murphy USA | [5 empty] | gaven.ballinger@murphyusa.com
Contact name & title |  | Kevin Parker |  |  |  | Gaven Ballinger/Terry Rigdon
e-mail |  | kparker@agoc.com |  |  |  | gaven.ballinger@murphyusa.com
Contact Phone # |  | 602-385-4100 |  |  |  | terryrigdon@murphyusa.com
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 10:30 AM/10:35 AM |  |  |  |  | Rain
Construction Phase: |  | Stabilization | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 78 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-06-28 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Install BMP's until the disturbed area on the North side is fully stabilized.
2 | No posting of NOI permit coverage. Post signage of NOI permit coverage in a location clearly visible to the public.
3 | Self-inspection report not provided upon last request.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | Mulch is still visible, but no growth.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action