## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E065 |  | Project Name: |  | Route 66 Flats
NPDES Id. No. | NMR1006EH |  | Location: |  | 7600 Central Ave SW
2025-07-21 |  | Owner |  |  |  | Contractor
Operator |  | Route 66 Flats, LLLP |  |  |  | FCI Constructors, Inc.
Contact name & title |  | Ashley Grant |  |  |  | James Harris
e-mail |  | ashley@bluelinedevelopment.com |  |  |  | jharris@fcinmllc.com
Contact Phone # |  | 406-529-5898 |  |  |  | 505-444-0663
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | Verticals, concrete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-07-03 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washout - There is evidence of illicit washout near a drain inlet in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-07-16
Notes:
Electronic SWPPP. Previous SWPPP violations have been mitigated.
Please check perimeter silt fencing after recent high winds.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action