## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E066 |  | Project Name: |  | D&B U Sell It
NPDES Id. No. | NMR1006GO & 69D |  | Location: |  | 401 Unser Blvd. and 8530 Bluewater Rd. NW
2025-01-27 |  | Owner |  |  |  | Contractor
Operator |  | D&B Limited Trust, LLC |  |  |  | Alliance Paving Company
Contact name & title |  | Miriam Ruiz |  |  |  | Jose L. Flores & Joseph Cruz
e-mail |  | miriamruiz@yahoo.com dblimitedtrust@gmail.com |  |  |  | jflores@allianceconinc.com
Contact Phone # |  | 505-884-3578 |  |  |  | 505-991-2467
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 215pm |  |  |  | Rain
Construction Phase: |  | Grading, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP and self-inspection reports were missing from the bucket on the back of the posting sign in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all self-inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
I talked with the superintendent who stated that the extra copy of the SWPPP will be brought up-to-date and delivered to the site (in the bucket).
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action