## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E066 |  | Project Name: |  | D&B U Sell It
NPDES Id. No. | NMR1006GO & 69D |  | Location: |  | 401 Unser Blvd. and 8530 Bluewater Rd. NW
2025-06-03 |  | Owner |  |  |  | Contractor
Operator |  | D&B Limited Trust, LLC |  |  |  | Alliance Paving Company
Contact name & title |  | Miriam Ruiz |  |  |  | Jose L. Flores & Joseph Cruz
e-mail |  | miriamruiz@yahoo.com dblimitedtrust@gmail.com |  |  |  | jflores@allianceconinc.com
Contact Phone # |  | 505-884-3578 |  |  |  | 505-991-2467
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Grading, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-02 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP and self-inspection reports were missing from the bucket on the back of the posting sign in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all self-inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | Sediment has been discharged into the intersection of Unser Blvd and Bluewater Rd due to a failure of the silt fence in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage per CGP Part 2.1.4. Remove the deposited sediment by sweeping, shoveling, or vacuuming. You are prohibited from hosing or sweeping the material into any constructed or natural drainage feature.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The SWPPP bucket has no lid and has water in it.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action