## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K10E066 |  | Project Name: |  | D&B U Sell It
NPDES Id. No. | NMR1006GO & 69D |  | Location: |  | 401 Unser Blvd. and 8530 Bluewater Rd. NW
2024-06-17 |  | Owner |  |  |  | Contractor
Operator |  | D&B Limited Trust, LLC |  |  |  | Alliance Paving Company
Contact name & title |  | Miriam Ruiz |  |  |  | Jose L. Flores & Joseph Cruz
e-mail |  | miriamruiz@yahoo.com dblimitedtrust@gmail.com |  |  |  | jflores@allianceconinc.com
Contact Phone # |  | 505-884-3578 |  |  |  | 505-991-2467
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 10:00 |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 99 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs— The pond(s) volume looked too small and was located east of the concentrated flow path, which appears to exit the site west of the small pond in violation of CGP 2.1.2. The pond installation was incomplete in violation of CGP 2.1.3, with inadequate volume, concentrated flow path bypasses the pond, and the overflow wasn't stabilized. Sediment Trap design volume calculations and Construction specifications were missing in violation of CGP 2.2.12 and the city's ESC Plan checklist. Required Mitigation: CGP Part 2.1.2 requires you to design and install all stormwater controls in accordance with good engineering practices, including applicable design specifications. You must finish the sediment basin design per CGP 2.2.12, including design calculations and construction specifications. The ESC Plan and pond design must be submitted to the City of Albuquerque for review and approval per Albuquerque’s Erosion and Sediment Control (ESC) ordinance § 14-5-2-11. You must also complete the installation before the next city inspection per the city ordinance and the escalation process. You must also ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage, per CGP Part 2.1.4. If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day per CGP 2.1.4.b. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational or complete the repair by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2024-05-29
Notes:
The vegetation had been removed from the entire site and construction had commenced. No personel or equipment was onsite. The SWPPP is in a bucket on the back of the sign.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action