## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K14E017 |  | Project Name: |  | Legacy Central and Broadway Hotel
NPDES Id. No. | NMR1001MD |  | Location: |  | SW Corner of Central and Broadway | [5 empty] | mferreira@legacydnm.com
2021-07-08 |  | Owner |  |  |  | Contractor
Operator |  | Legacy Hospitality |  |  |  | Kassam Construction, LLC
Contact name & title |  | Faisel Kassam |  |  |  | Matt Ferreira
e-mail |  | fkassam@legacy-hospitality.com |  |  |  | mferreira@kassamconstruction.com
Contact Phone # |  | 505-243-6000 |  |  |  | 505-415-4568
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:05 AM-11:30 AM |  |  |  | Rain
Construction Phase: |  | Building construction, flatwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-07-06 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Sediment in west channel. Remove accumulated sediment daily from the channel on the West side of the site and from the streets. | [9 empty] | 2021-05-03
2 | Washout on the ground. Direct washwater into a leak-proof container and dispose of properly in a an approved waste container.
3 | Self-inspection reports not in the SWPPP and not provided upon last request.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-03-10
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action