## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K15E005G |  | Project Name: |  | PHS SE Parking Garage
NPDES Id. No. | NM1002V2 |  | Location: |  | 1300 Central Ave. SE | [5 empty] | Cornish, Eric <ecornish@phs.org>
2021-04-27 |  | Owner |  |  |  | Contractor
Operator |  | Presbyterian Healthcare Services |  |  |  | Enterprise Builders |  |  |  |  | Anthony Crump
Contact name & title |  | Jim Jeppson |  |  |  | Mike Bertitto
e-mail |  | JJeppson@phs.org |  |  |  | mbertetto@ebnm.com |  |  |  |  | Mike Bertetto - Superintendent | mbertetto@ebnm.com
Contact Phone # |  | 505-841-1769 |  |  |  | 505-264-3961
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 3:20 PM/4:15 PM |  |  |  |  | Rain
Construction Phase: |  | Vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 62 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-04-28 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Wattles were not covering the length of the fence in some areas. Reposition wattles to prevent any discharge of sediment.
2 | Waste/debris accumulation in the SW corner of the site where the wattle is not properly positioned. Clean the area and reposition wattle.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-04-26
Notes: | Spoke with Superintendent Mike Bertitto. SWPPP is kept onsite in the trailer. The latest
self-inspection report was conducted on Monday, April 26, and recurring inspections are every
Monday. Green Globe retains the reports electronically. Site is expected to be completed in the next
3-4 months.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action