## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K15E034 |  | Project Name: |  | Highlands Tracts 4, 5, and 6
NPDES Id. No. | NMR1006CH |  | Location: |  | 1313 Central Ave NE
2024-12-19 |  | Property Owner |  |  |  | Contractor
Operator |  | Cedar Investments, LLC CO Argus Dev.
Contact name & title |  | Josh Rogers/Matt Lammers
e-mail |  | jrogers@titan-development.com
Contact Phone # |  | 505-998-0163 505-515-2901
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | graded, inactive | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-11-11
Notes:
The sediment along Cedar St has reduced to a shadow. The sediment in the driveway curb should be cleared to prevent more sediment runoff into the street. The stabilization comments will be withheld while you await approval for the project developing the remainder of Tract 4.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action