## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K15E034 |  | Project Name: |  | Highlands Tracts 2 & 6
NPDES Id. No. | NMR1003OP |  | Location: |  | 1015 and1315 Central Ave NE
2024-03-25 |  | Delegated Authority |  |  |  | Responsible corporate Officer
Operator |  | Cedar Investments, LLC CO Argus Dev. |  |  |  | Cedar Investments, LLC CO Argus Dev.
Contact name & title |  | Josh Rogers |  |  |  | Matt Lammers
e-mail |  | jrogers@titan-development.com |  |  |  | mlammers@titan-development.com
Contact Phone # |  | 505-998-0163 505-515-2901 |  |  |  | 505-998-0163
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 1:50 PM-2:00 PM |  |  |  | Rain
Construction Phase: |  | idle | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 88 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-05-31 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI (NMR1003OP) expired. Required Mitigation: The property owner’s NOI and ESC Plan must be submitted to the City of Albuquerque for review and approval per Albuquerque’s Erosion and Sediment Control (ESC) ordinance § 14-5-2-11
2 | Posting was missing. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
3 | Sediment in Cedar Street. Sweep and remove sediment on the streets/sidewalks.
4 | SWPPP and self-inspection reports were not available onsite during the inspection in violation of CGP
5 | BMPs
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | No activity on the site during this inspection. West tract is being used for hotel parking.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action