## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K15E034A |  | Project Name: |  | Broadstone North Block
NPDES Id. No. | NMR1000VI - NMR1001FJ |  | Location: |  | 1111 Copper Ave NE
2020-12-29 |  | Property Owner |  |  |  | Contractor
Operator |  | Cedar Investments, LLC CO Argus Dev. |  |  |  | Alliance Residential Builders
Contact name & title |  | Josh Rogers |  |  |  | Lee Riley
e-mail |  | jrogers@titan-development.com |  |  |  | lriley@allresco.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-264-7022
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8am |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2020-12-11 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Sediment in Street trackout and leaks under silt fence on Cedar. Please remove sediment.
2
3
4
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2020-12-25
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action