## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K15E034D |  | Project Name: |  | Residence Inn & Food Hall ABQ
NPDES Id. No. | NMR1006YF |  | Location: |  | 1201 Central Ave NE
9/23/25; 9/26/25 |  | Owner |  |  |  | Contractor
Operator |  | Cedar Investors, LLC
Contact name & title |  | Matt Lammers
e-mail |  | mlammers@titan-development.com
Contact Phone # |  | 505-998-0163
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-09-14 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP was unavailable at the time of the inspection in violation of CGP Part 7.3. Required mitigation: You must keep a current copy of your SWPPP at the site or at an easily accessible location so that it can be made immediately available at the time of an on-site inspection per CGP Part 7.3.
2 | BMPs - The perimeter silt fencing is not properly entrenched on the north side of the property in violation of CGP Part 2.1.2. A storm discharge pipe has no inlet protection and is half full of sediment in violation of CGP Parts 2.1.3 and 2.2.10. Required mitigation: Design and install all stormwater controls in accordance with good engineering practices, including applicable design specifications pre CGP Part 2.1.2. Complete installation of stormwater controls by the time each phase of construction has begun per CGP Part 2.1.3. Install inlet protection measures that remove sediment from discharges prior to entry into any storm drain inlet that carries stormwater from your site to a receiving water per CGP Part 2.2.10. Remove the deposited sediment by the end of the same business day in which it is found.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-09-22
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action