## 04.2019Form
City of Albuquerque | [7 empty] | Inspection: | Weather: | Violation: | Reports: | Discharge: | ROW: | Yes/No/NA
Stormwater, Erosion, and Sediment Control | [7 empty] | Inspection | Weather | Violation | Reports | Discharge | ROW Type | Yes/No/NA
Construction Site Inspection Report | [13 empty] | Yes
General Information | [7 empty] | Pre-Construction | Ice | None | Yes | Shadow | Other | No
ESC File #: |  | K16E097 |  | Project Name: | Solana Apartments |  |  | Routine | Hail | NOI | No | Yes | Sidewalk | N/A
ABQ-PLAN #: |  | SWQ-2025-00064 |  | Project Address: | 208 Wellesley Dr SE |  |  | Follow-up | Snow | Posting | Requested | No | Street
NPDES ID #: |  | NMR1007L0 |  | Inspection Type: | Routine |  |  | 311/Complaint | Clear | SWPPP | Out-of-date |  | Storm Drain Inlet
2026-03-09 |  | Owner |  |  | Contractor |  |  | Storm Event | Rain | BMPs | Unsigned |  | Drainage Ditch
Operator: |  | C3 Residential LLC |  |  | American Realcorp Construction Services, Inc. |  |  | Post Storm Even >0.25" | Clear/Windy | Sediment |  |  | Arroyo
Contact Name: |  | Robert Cohen |  |  | Dan Loy |  |  |  | Windy | Washout |  |  | Private Property
Contact e-mail: |  | rcbuilds73@gmail.com |  |  | laso1@me.com |  |  |  | Cloudy | Litter |  |  | N/A
Contact Phone: |  | 949-423-5560 |  |  | 505-991-2089 |  |  |  | Sleet | Porta-potty
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 2026-03-09 | Time of Inspection: | 12pm |  |  | Stabilization
NPDES Posting? |  | No | SWPPP? | Yes | Notice of Intent? | Yes
Self-Inspection Reports? |  |  | Out-of-date | Date of last report: | 2026-01-26
Weather during inspection: |  |  | Clear | Estimated date of last storm 0.25" or greater: |  | 2026-01-25 | Snow
Temperature: ~ |  | 60 | Construction Phase: | Grading
Discharge off-site? |  | No | ROW: | N/A
Item # | Violation Category | Deficiency/Corrective Action
1 | Posting | The CGP coverage posting was not mounted where the public can view it in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site.
2 | SWPPP | The inspection reports available on-site were not up-to-date in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Notes:
The Delegation of Authority pages have been signed, but they are blank and do not assign authority to anyone. The superintendent can sign for American Realcorp Construction once the pages are completed.
The NOI for the contractor (NMR1007NI) is still "on hold" from the EPA.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action