## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K17E073 |  | Project Name: |  | Nob Hill Apartments Urban Living
NPDES Id. No. | NMR1001V0 |  | Location: |  | 4101 Central Avenue NE | [5 empty] | Michael Davis <medavis@allresco.com>
2021-05-11 |  | Owner |  |  |  | Contractor
Operator |  | Titan Development |  |  |  | Alliance Residential Buildiers |  |  |  |  | Lee Riley <lriley@allresco.com>
Contact name & title |  | Kurt Browning |  |  |  | Lee Riley
e-mail |  | kbrowning@titan-development.com |  |  |  | lriley@allresco.com |  |  |  |  | Jeff Hart <jeff@inspectionsplus.com>
Contact Phone # |  | 505-998-0163 |  |  |  | 505-264-7022
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:25 PM/1:55 PM |  |  | Brian Patterson <bpatterson@Titan-Development.com> | Rain
Construction Phase: |  | Building construction/landscaping | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up | Bob Kearney <bkearney@titan-development.com> | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 76 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Sediment accumulation in the street at the inlet. Remove sediment from the inlet area and maintain inlet protection. | [9 empty] | 2021-05-03
2 | Washout on the ground. Direct wash water from concrete, paint, and stucco into a leak-proof container per CGP 2.3.4. Remove and dispose of hardened washout.
3 | Trackout in the streets. Sweep the streets and sidewalks daily to prevent sediment from entering the street.
4 | No sediment control BMPs installed along fenclines. Install silt fences as detailed in the ESC Plan to prevent sediment from exiting the site.
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-04-03
Notes: | Mike Davis told me base course was coming in next week and paving will be starting soon.
Silt fences along Central were taken down during work on the sidewalks/landscaping.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action