## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K17E120 |  | Project Name: |  | Highland Plaza Apartments
NPDES Id. No. | NMR10049J |  | Location: |  | 5000 Central Av SE
2022-08-16 |  | Owner |  |  |  | Contractor
Operator |  | Greater Albuquerque Housing Partnership |  |  |  | Jaynes Corp
Contact name & title |  | Felipe Rael |  |  |  | Jose Garcia
e-mail |  | Felipe@abqGahp.org |  |  |  | Jose.Garcia@jaynescorp.com
Contact Phone # |  | 980-5922 |  |  |  | 362-0409
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 12:30-1:30 PM |  |  |  | Rain
Construction Phase: |  | Staging | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-08-01 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The lined washout pit seemed effwective but some wasout was noted at several other locations. Pickup and dispose of dried washout and instruct all subs to use the lined container. | [9 empty] | 2021-05-03
2 | Tracked out sedimant in Silver street needs picked up. Remove dirt ramp. Sweep street promptly if more trackout occurs. Also clean sidewal on Jackson and repair SF and mulch sock. | [9 empty] | 2021-05-31
3 | SWPPP was mostly up-to-date. The 2022 CGP was missing. Replace the 2017 CGP with the 2022 | [9 empty] | 2021-06-28
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | required | Latest report Date: |  | 2022-08-16
Notes: | SWPPP in trailer next door to site. Jose is DA.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action