## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K19E005 |  | Project Name: |  | CABQ International District Library
NPDES Id. No. | NMR10031F |  | Location: |  | 7667 Central NE
2021-05-11 |  | Owner |  |  |  | Contractor |  |  |  |  | Matt Vallejos |  | Greenglobe | matt@greenglobenm.com
Operator |  | City of Albuquerque |  |  |  | Bradbury Stamm |  |  |  |  | Stacy Herrera | CABQ | stacyherrera@cabq.gov
Contact name & title |  | Sherry Keefe |  |  |  | Darren Mortensen
e-mail |  | skeefe@cabq.gov |  |  |  | dmortensen@bradburystamm.com
Contact Phone # |  | 505-768-3830 |  |  |  | 505-681-2475
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 12:10 PM/12:35 PM | [6 empty] | Rain
Construction Phase: |  | Building construction | [12 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 74 | [5 empty] | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [14 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | None. | [9 empty] | 2021-05-03
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | Not on file
Notes: | Spoke with Darren. SWPPP on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action