## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Maverik
Location: |  |  | 650 Juan Tabo
Site Contact Name & Agency |  |  | Jason - Insight Const |  |  |  | ESC File No. | K22E059
|  |  | jason@insisghtnm.com |  |  |  | NPDES Id. No. | NMR10022L
Inspection Date: |  |  | 2019-10-17 | Start/End Time: |  | 0800/0820hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 55* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2019-10-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Mitigate all washouts on site. North of refuse bin, south of building, and at Superintendent's
trailer. Ensure trades utilize provided washout facility. This facility may need to be relocated
closer to work site or provide a secondary location.
2 | Trackout on Zia, from entrance to Paisano requires removal. A follow up inspection will occur
tomorrow. (Trackout is required to be removed daily.)
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports | [5 empty] | Latest report Date: |  | 2019-10-07
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2019-10-17

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action