## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L09E042 |  | Project Name: |  | Mercado El Milagro
NPDES Id. No. |  |  | Location: |  | 10000 Central Ave SW
2021-01-27 |  | Owner
Operator |  | PPI II, LLC
Contact name & title |  | Doug Peterson
e-mail |  | doug@petersonproperties.net
Contact Phone # |  | 884-3578
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 4:30pm |  |  |  | Rain
Construction Phase: |  | infrastructure complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2020-12-11 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The Owner's NOI is missing, inspection fees are not paid. A new SWQ submital is required
2 | 1.5 acre staging area has no stabilization and must be stabilized per CGP 2.2.14
3 | BMPs are missing. Ensure that all stormwater controls (BMPs) are maintained and remain in effective operating condition during permit coverage per CGP 2.1.4.
4 | Permits were not posted. Post coverage per CGP 1.5
5 | Please provide the latest self-inspection report.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
Notes:
Contractor filed NOT 9/6/2019 without sucessor operator or final stabilization, which
violates CGP 8.2. The property owner paid for plans and is an operator but failed to file NOI.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action