## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L09E042A |  | Project Name: |  | Mercado El Milagro Bldg. D & Bldg. G
NPDES Id. No. | NMR10056E/NMR1005MD |  | Location: |  | 10000 Central Ave SW
9/19, 9/24/2024 |  | Owner |  |  |  | Contractor
Operator |  | PPI II, LLC |  |  |  | Wilger Enterprises
Contact name & title |  | Doug Peterson |  |  |  | John Wilger
e-mail |  | doug@petersonproperties.net |  |  |  | jwilger@wilger.com
Contact Phone # |  | 505-884-3578 |  |  |  | 505-345-2854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1PM |  |  |  | Rain
Construction Phase: |  | Building D complete but no power, Building G graded and inactive | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-08-31 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The site was missing permit coverage posting for Building G in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site, as per CGP Part 1.5.
2 | SWPPP - Either the SWPPP for Building G is missing or the SWPPP for Building D is not up-to-date in violation of either CGP Part 7.3 or 7.4. The self-inspection reports are not current for Building D and missing for Building G in violation of CGP Part 4.7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. You must modify your SWPPP, including the site maps, within seven days whenever new operators become active in construction activities on your site, or you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1.a.
3 | Stabilization - The land disturbances for both Building D and Building G have been inactive for several months without any stabilization measures installed in violation of CGP Part 2.2.12. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the installation of stabilization measures as soon as practicable, but no later than 14 calendar days per CGP Part 2.2.14.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-06-24
Notes:
This inspection report is for 2 NOIs for the same owner: Building D - NMR10056E and Building G - NMR1005MD
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action