## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L09E042A |  | Project Name: |  | Mercado El Milagro Bldg. D (Federidelfo's)
NPDES Id. No. | NMR10056E |  | Location: |  | 10000 Central Ave SW
2025-02-24 |  | Owner |  |  |  | Contractor
Operator |  | PPI II, LLC |  |  |  | Wilger Enterprises
Contact name & title |  | Doug Peterson |  |  |  | John Wilger
e-mail |  | doug@petersonproperties.net |  |  |  | jwilger@wilger.com
Contact Phone # |  | 505-884-3578 |  |  |  | 505-345-2854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Building D complete, needs stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The most current self-inspection report that was available on-site was 6/25/24 and it appears that the inspections have ceased in violation of City Ordinance §14-5-2-11. The owner's NOI is still active. Required mitigation: At a minimum, a routine compliance self-inspection is required to review the project for compliance with the CGP once every 14 days and after any precipitation event of 1/4 inch or greater until the site construction has been completed and the site determined as stabilized by the City. Reports of these inspections shall be kept by the person or entity authorized to direct the construction activities on the site and shall be conducted during progress of the work, during work suspensions, and until final acceptance of site stabilization by the City per City Ordinance §14-5-2-11 Paragraph (C)-1.
2 | The southeast portion of the site has been inactive and has no stabilization measures installed in violation of CGP Part 2.2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where the construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the installation of stabilization measures as soon as practicable, but no later than 14 calendar days per CGP Part 2.2.14.a.
3
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-06-25
Notes:
The SWPPP for Building D is in the construction office for Building G
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action