## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L10E030 |  | Project Name: |  | Sage Park Subdivision
NPDES Id. No. | NMR1006LM |  | Location: |  | 6601 Sage Rd SW
2025-03-05 |  | Owner |  |  |  | Contractor
Operator |  | Stillbrooke Homes
Contact name & title |  | Chris Kelsey
e-mail |  | ckelsey@stillbrooke.com
Contact Phone # |  | 505-585-1800
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 130pm |  |  |  | Rain
Construction Phase: |  | Grading, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | None
Check and repair the perimeter silt fence. Recent high winds have pulled some stakes out of the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-02-10
Notes:
The SWPPP is located in the box mounted on the back of the Stillbrooke sign.
Cut-back curbs, silt fence, and the sediment pond likely prevents any stormwater discharge onto Sage Rd.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action