## 04.2019Form
|  | City of Albuquerque ---Stormwater Construction Site Inspection Report--- | [8 empty] | Weather: | Discharge: | Reports: | ROW:
General Information | [11 empty] | Shadow | Yes
ESC File # | L10E030 |  | Project Name: |  |  | Sage Park Subdivision | [5 empty] | Yes | No
NPDES ID # | NMR1006LS |  | Location: |  |  | 6601 Sage Rd SW | [5 empty] | No | Requested | Sidewalk
2026-02-23 |  | Owner |  |  |  |  | Contractor |  |  |  | Snow |  | Out-of-date | Street
Operator |  | Stillbrooke Homes | [8 empty] | Clear |  | Unsigned | Storm Drain Inlet
Contact name & title |  | Chris Kelsey | [8 empty] | Rain |  |  | Drainage Ditch
Contact e-mail |  | ckelsey@stillbrooke.com | [8 empty] | Clear/Windy |  |  | Arroyo
Contact Phone # |  | 505-585-1800 | [8 empty] | Windy |  |  | Private Property
COA Inspector |  | Chancellor English |  |  |  |  | Start/End Time: |  | 12:15pm |  | Cloudy |  |  | N/A
Construction Phase: |  | 6 houses started | [8 empty] | Sleet
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up
Weather at time of inspection: |  |  |  | Clear |  | Temperature: ~ |  | 50
Estimated date of last storm 0.25" or greater: |  |  |  |  | 2026-01-08
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The inspection reports were not up-to-date in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | Washout - There is a pile of concrete washout on bare ground in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so that no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Discharge off-site? |  | No | Right-of-way: |  |  | N/A
Self-Inspection Reports? |  | Yes | Latest report Date: |  |  | 2025-12-01
Notes:
The SWPPP is mounted on the back of the Stillbrooke sign next to the CGP Posting.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action