## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L14E068 |  | Project Name: |  | El Mezquite Market Renovation
NPDES Id. No. | NMR100782 |  | Location: |  | 1306 Broadway Blvd SE
2025-10-08 |  | Owner |  |  |  | Contractor
Operator |  | Bermudez Bros LLC |  |  |  | Mountain Side Contractors LLC
Contact name & title |  | Sergio Bermudez |  |  |  | Aldo Ornelas
e-mail |  | sergiob@elmezquitemarket.net |  |  |  | mountainsidecontractors@gmail.com
Contact Phone # |  | 505-975-5175 |  |  |  | 505-227-1782
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1045am |  |  |  | Rain
Construction Phase: |  | Demolition | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - Your inspection reports were not available during the inspection in violation of CGP Part 4.7.3. The contractor's NOI was missing from the SWPPP in violation of CGP Part 7.2.11. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made available at the time of an on-site inspection per CGP Part 4.7.3. Once you are authorized for CGP coverage, you must include a copy of your NOI submitted to the EPA per CGP Part 7.2.11.a.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The gate lock combo is 0715.
The SWPPP is in a display case in the main building.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action