## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L15E057_UNM |  | Project Name: |  | Alumni Drive Extension
NPDES Id. No. | NMR1006TZ LEW |  | Location: |  | Alumni Dr and Gibson SE
2025-04-23 |  | Owner |  |  |  | Contractor
Operator |  | University of New Mexico |  |  |  | Compass Engineering & Construction Services, LLC
Contact name & title |  | Teresa Costantinidis |  |  |  | William Lucero
e-mail |  | keelie@unm.edu |  |  |  | will@compassnm.com
Contact Phone # |  | 505-227-7520 |  |  |  | 505-221-6003
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Pre-paving | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-04-20 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The Erosion and Sediment Control Permit was not posted at the site in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | According to the superintendent of the site, there have been no self-inspections performed during construction in violation of City Ordinance 14-5-2-11 and CGP Part 4.2. Required mitigation: At a minimum, a routine self-inspection is required to review the project for compliance with the Construction General Permit once every 14 days and after any precipitation event of 1/4 inch or greater until the site construction has been completed and the site determined as stabilized by the City per City Ordinance 14-5-2-11 and CGP Part 4.2.2.
3 | The silt fence and mulch socks were not installed according to the ESC Plan approved by the City in violation of CGP Part 2.1.3. Required mitigation: Complete installation of stormwater controls by the time each phase of construction activities has begun per CGP Part 2.1.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The ESC Permit approved by the City expired on April 1, 2025, although a search of the EPA database shows that the LEW was amended to extend the coverage through May. Performing land-disturbing activities without permit coverage can result in Formal Violations and financial penalties.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action