## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L19E023 |  | Project Name: |  | C&D Storage | [6 empty] | Gary Christensen
NPDES Id. No. | NMR1004BT/NMR1003GJ |  | Location: |  | 423 Wyoming Blvd SE | [5 empty] | Roy Solomon | 720-8475
2023-04-05 |  | Owner |  |  |  | Contractor
Operator |  | C&D Land Corp. |  |  |  | Wilger
Contact name & title |  | Chris DiJulio |  |  |  | Scot McLelland
e-mail |  | chrisd@lincmove.com |  |  |  | scot@wilger.com
Contact Phone # |  | 206-226-5252 |  |  |  | 345-2854
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 10:30am |  |  |  |  | Rain
Construction Phase: |  | Stabilization/inactive | [10 empty] | Clear/ Windy
Type of Inspection: |  | regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 40 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-16 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | none - The site satisfes the final stabilization Criteria of CGP 2.2.14.c (all paving and roof) | [9 empty] | 2021-05-03
2 | You must file your NOT following the procedure in section 8 of the CGP. Copy me with documentation showing the NOT has been accepted by the EPA. | [9 empty] | 2021-05-31
3
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | ??? | Latest report Date: |  | none
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action