## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L20E075 |  | Project Name: |  | JB Henderson New Fabrication Facility
NPDES Id. No. | NMR1003Q6 |  | Location: |  | 10200 Bell Avenue SE
2021-07-14 |  | Owner |  |  |  | Contractor
Operator |  | Trumbull Development, LLC. |  |  |  | JB Henderson
Contact name & title |  | John Stroud |  |  |  | Jim Kaiser
e-mail |  | jstroud@jbhenderson.com |  |  |  | jkaiser@jbhenderson.com
Contact Phone # |  | 505-292-8955 |  |  |  | 505-975-1462
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:40 AM-12:15 PM |  |  |  | Rain
Construction Phase: |  | Earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 84 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-07-06 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Track-out in the streets. Sweep and remove sediment daily.
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | SWPPP is up-to-date. Spoke with Jim Kaiser, and he will have somebody sweep up the
track-out as soon as possible. Inspection reports are in the SWPPP
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action