## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L21E045C |  | Project Name: |  | Luminaria Senior Community
NPDES Id. No. | NMR1003H0 |  | Location: |  | 10600 Central Ave.
2021-06-03 |  | Owner |  |  |  | Contractor
Operator |  | Greater Albuquerque Housing Partnership |  |  |  | Jaynes Corp
Contact name & title |  | Felipe Rael |  |  |  | Jeff Harper |  |  |  |  | Green Globe
e-mail |  | felipe@abqGAHP.org |  |  |  | jeff.harper@jaynescorp.com |  |  |  |  | Matt Vallejos
Contact Phone # |  | 505-980-5922 |  |  |  | 505-250-9351
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:10 PM-1:35 PM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 84 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Track-out pad needs maintenance. Add additional rock to track-out pad | [9 empty] | 2021-05-03
2 | No perimeter BMP along North fence line. Install perimeter BMP as described in the ESC plan. | [9 empty] | 2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | Green Globe to send
Notes: | Jeff said that the track-out pad is scheduled for maintenance next week and that he will
re-install the perimeter BMP on the North side.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action