## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L21E074 |  | Project Name: |  | Farolito Senior Community
NPDES Id. No. | NMR1005Y8 |  | Location: |  | 10501 Central Ave NE
2024-11-05 |  | Owner |  |  |  | Contractor
Operator |  | Farolito Apartments Limited Partnership LLLP |  |  |  | Jaynes Corporation
Contact name & title |  | Felipe Rael |  |  |  | Shad James
e-mail |  | felipe@solhousing.org |  |  |  | shad.james@jaynescorp.com
Contact Phone # |  | 505-980-5922 |  |  |  | 505-345-8591
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 230pm |  |  |  | Rain
Construction Phase: |  | none, weeds and partial land disturbance | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The posting was on-site in the construction office, and was not posted in a publicly accessible area in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | Sediment has been tracked out of the site onto Central Ave in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited sediment by the end of the same business day per CGP Part 2.2.4.
3 | The NOI included in the SWPPP is for Greater Albuquerque Housing Partnership and needs to be amended to the Farolito Apartments Limited Partnership LLLP to match the Lease and Building Permit information in violation of CGP Part 1.4.4. The NOI for Jaynes Construction also needs to be included in the SWPPP in violation of CGP Part 7.2.11. Required mitigation: Modify your NOI if there are changes to the name of the operator per CGP Part 1.4.4. Once you are authorized for coverage under the CGP, you must include a copy of your NOI submitted to EPA along with any correspondence exchanged between you and EPA related coverage under the CGP per CGP Part 7.2.11
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-10-30
Notes:
Green Globe arrived on-site during the City's inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action