## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L23E022 |  | Project Name: |  | Beehive Four Hills
NPDES Id. No. | NMR1001RX |  | Location: |  | 13450 Wenonah Ave. SE
2021-07-01 |  | Owner |  |  |  | Contractor
Operator |  | Host Care, LLC. |  |  |  | S & J Ent.
Contact name & title |  | Jerry Castillo |  |  |  | Jason Castillo
e-mail |  | Castillofour@msn.com |  |  |  | jasoncastillo88@gmail.com
Contact Phone # |  | 505-884-6243
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 8:45 AM-8:55 AM |  |  |  | Rain
Construction Phase: |  | idle/stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 73 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-06-28 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | No posting of NOI permit coverage. Post signage of NOI permit coverage in a location clearly visible to the public.
2 | Holes in silt fence. Repair/miantain silt fences.
3 | Maintain BMPs for stabilization. Identify stabilization controls implemented on the East and Central sections of the site.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2019-12-27
Notes: | Need to confirm the status of stabilization on the East half of the site. A section of silt
fence was repaired at the NE corner of the middle section.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action