## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | L23E022 |  | Project Name: |  | Beehive Four Hills
NPDES Id. No. | NMR1001RX |  | Location: |  | 13450 Wenonah Ave. SE
2022-09-09 |  | Owner |  |  |  | Contractor
Operator |  | Host Care, LLC. |  |  |  | S & J Ent.
Contact name & title |  | Jerry Castillo |  |  |  | Jason Castillo
e-mail |  | Castillofour@msn.com |  |  |  | jasoncastillo88@gmail.com
Contact Phone # |  | 505-884-6243
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 15:10 |  |  |  | Rain
Construction Phase: |  | idle/stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 88 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-08-21 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The stabilization on this site satisfies the final stabilization criteria CGP 2.2.14, even a couple of pad sites have been covered in gravel.
2 | The EPAs web site shows permit coverage expired. Please file the Notice of Ternination (NOT) with the EPA.
3 | Future EPA permit coverage will not be required for the two remaining pad sites when they go to Building Permit because the entire "Common Plan of Development" is stabilized according to Google Earth street view dated 4/22.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | n/a
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action