## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E012 |  | Project Name: |  | Sage Plaza
NPDES Id. No. | NMR1005QA |  | Location: |  | 1125 Snow Vista Blvd
2023-10-30 |  | Owner |  |  |  | Contractor
Operator |  | Goodman Realty RVT |  |  |  | Cornerstone Contractors
Contact name & title |  | Scott Goodman |  |  |  | Joseph Nevarez
e-mail |  | sgoodman@goodmanrealty.com |  |  |  | joseph@cornerstoneNM.com
Contact Phone # |  | 505-441-2354 |  |  |  | 505-385-7746
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10am |  |  |  | Rain
Construction Phase: |  | infrastructure nearly complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-09-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The contractor was not identified in the SWPPP. The stormwater team needs to be identified by name and have contact information. A record of training or training certificates for the stormwater team was missing. The SWPPP map was not current by not showing the areas left undisturbed.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-10-18
Notes:
In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action