## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E012 |  | Project Name: |  | Sage Plaza
NPDES Id. No. | NMR1005QA |  | Location: |  | 1125 Snow Vista Blvd
2023-11-22 |  | Owner |  |  |  | Contractor
Operator |  | Goodman Realty RVT |  |  |  | Cornerstone Contractors
Contact name & title |  | Scott Goodman |  |  |  | Joseph Nevarez
e-mail |  | sgoodman@goodmanrealty.com |  |  |  | joseph@cornerstoneNM.com
Contact Phone # |  | 505-441-2354 |  |  |  | 505-385-7746
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 930am |  |  |  | Rain
Construction Phase: |  | stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-11-20 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP was not available at the time of inspection in violation of CGP Part 7.3. The contact information on the permit coverage posting is no longer correct. The latest inspection report available was dated a month ago, in violation of CGP Part 4.2 and City Ordinance 14-5-2-11. Required mitigation: You must keep a copy of all inspection reports and the current SWPPP at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. At a minimum, you must conduct a site inspection once every 14 calendar days and within 24 hours of a storm event that produces 0.25 inches or more of rain until the site construction has been completed and the site determined as stabilized by the City per CGP Part 4.2 and City Ordinance 14-5-2-11.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-10-18
Notes: | Hydromulch has been applied
In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action