## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E012B |  | Project Name: |  | 98th & Sage Storage Frontera
NPDES Id. No. | NMR10066R |  | Location: |  | 9850 De Vargas Rd SW
2024-08-23 |  | Owner |  |  |  | Contractor
Operator |  | FRE Albuquerque SS, LLC
Contact name & title |  | Bryan Grissinger & Todd Megrath |  |  |  | David Harvey & Ian Ring
e-mail |  | bryan@fronteerarearealestate.com
Contact Phone # |  | 619-756-4622 |  |  |  | 913-302-7409
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1PM |  |  |  | Rain
Construction Phase: |  | foundations | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were unavailable at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep an up-to-date SWPPP and copies of all inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | Washout - The concrete washout measures were over capacity; the washout pit has overflowed and allowed concrete washout on bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground per CGP Part 2.3.4.
3 | Sediment - The construction entrance was inundated with dirt causing track-out onto the access road in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which track-out occurs or by the end of the next business day if track-out occurs on a non-business day. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces. You are prohibited from hosing or sweeping tracked-out sediment into any constructed or natural site drainage feature, storm drain inlet, or receiving water per CGP Part 2.2.4. | [9 empty] | Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
SWPPP is located in the Conex.
The superintendent was not on-site and the construction office was locked.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action