## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | M09E012B |  | Project Name: |  | 98th & Sage Storage Frontera
NPDES Id. No. | NMR10066R |  | Location: |  | 9850 De Vargas Rd SW
2/20-21/2025 |  | Owner |  |  |  | Contractor
Operator |  | FRE Albuquerque SS, LLC |  |  |  | GYS General Contracting
Contact name & title |  | Bryan Grissinger & Todd Megrath |  |  |  | David Harvey & lan Ring
e-mail |  | bryan@fronteerarearealestate.com |  |  |  | david.h@gysgeneralcontracting.com
Contact Phone # |  | 619-756-4622 |  |  |  | 719-510-4202 / 913-302-7409
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | paving | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP is not current - The SWPPP Map does not include the construction use of the neighboring property (vehicle and equipment parking, materials and waste) in violation of CGP Part 7.4.1 and the inspection reports available for inspection were not up-to-date in violation of CGP Part 4.7.3. The General Contractor and the neighboring property owner have NOIs that need to be included in the SWPPP in violation of CGP Part 7.2.11. Required mitigation*: You must modify your SWPPP, including the site map(s), within 7 days whenever you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1.a. You must keep a copy of all inspection reports at the site or at an easily accessible location so that it can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3. All operators must include, in the SWPPP, a copy of their NOI submitted to the EPA per CGP Part 7.2.11.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2024-08-28
Notes: | The SWPPP is located in the construction office
*There are 2 options for mitigating the violation related to construction activity occurring on the neighboring property: Either 1) provide the neighboring property owner's NOI and amend the SWPPP Map to reflect the usage (as stated above) or 2) remove all materials and equipment from the property and stabilize the disturbed land outlined in CGP Part 2.2.14.c.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-294-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action